## Simple Example
DAILY HOT COST |  |  |  | Date:
TO: |  |  | Day | 8 | of 23
FROM: |  |  | Location
EXEC PRODUCER: |  |  | Start Date | 2018-11-26
PRODUCER: |  |  | Finish Date | 2019-01-31
DIRECTOR: |  |  | Revised Finish Date | N/A
APPROX DAILY COST: | $40,000 |  | Ahead/(Behind)
Page Count Per Call Sheet: |  | 4.125 | Pages Shot Per Production Report: |  | 4.125
Scenes Scheduled per Call Sheet: |  | 29, 41, 5v | Scenes Shot Per Production Report: |  | 29, 41, 5v
Script Status | Pages | Scenes | Schedule | Days Scheduled | Actual To Date
Shot Today | 4.125 | 3 | Shooting Days | 23 | 6
Shot Previously | 18.875 | 23 | Holidays | 0 | 0
Total To Date | 23 | 26 | Travel Days | 0 | 0
Script Total | 80.375 | 119 | Ins Claim Days | 0 | 0
Added/Deleted | 0 | 0 | Idle Days | 0 | 0
Total Remaining | 57.375 | 93 | Totals | 23 | 6
| BUDGETED | ACTUAL | (OVER)/UNDER |  | APPROXIMATE COST
Crew Hours | 13 | 12 | 1 |  | 1050
Crew M P V | 0 | 0 | 0 |  | 0
Drivers Hours | 15 | 14 | 1 |  | 108
Standins | 3 | 3 | 0 |  | 0
Extras - N/U | 32 | 32 | 0 |  | 0
B T L Fringe |  |  |  |  | 23.16
Cast OT Hours | 1 | 0 | 1 |  | 1850
Cast Fringes
Catering Crew/Cast | 145 | 160 | -15 |  | -178.9279
Catering Extras/Security | 47 | 42 | 5 |  | 59.6426
Telecine | 0 | 0 | 0
Additional Items:
# 1 |  |  | 0
# 2 |  |  | 0
# 3 |  |  | 0
| Budget | 3753334 |  | Today's Variance | 2911.8747
| Approved Overage | 0 |  | Prior Cumulative Weekly Variance | 14883
| Total (Over) / Under | 0 |  | Total Weekly Variance | 17794.8747
| Estimated Final Cost | 3753334
(Producer/U P M Acknowledgement) |  |  |  | (Accountant Acknowledgement)
Put a description there if you have an item
For submission to the studio each day, you can just type names on these lines - (once UPM has approved) - that way's cleaner than faxing a copy with actual signatures.
Just get actual signatures on your copy that goes in show files.

## Detailed Example
Episode: |  |  |  |  | Director: |  |  |  | Report Date: | 2020-09-13 | STANDIN MANDAYS |  |  | CUMULATIVE | RAW STOCK |  |  | CUMULATIVE | PROCESSING |  |  | CUMULATIVE
Film Date: |  |  |  |  | Exec Producer: | [5 empty] | DAY | BDGT | ACTUAL | VARIANCE | DAY | BDGT | ACTUAL | VARIANCE | DAY | BDGT | ACTUAL | VARIANCE
Call Time: |  |  |  |  | Exec Producer: | [5 empty] | 1 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Camera Wrap Time: |  |  |  |  | Co-Exec Producer: | [5 empty] | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0
Location Wrap Time: |  |  |  |  | Co-Exec Prod: | [5 empty] | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0
Location: |  |  |  |  | Line Producer: | [5 empty] | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0
[5 empty] | UPM: | [5 empty] | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0
[5 empty] | Prod Acct: |  |  | Total Pages Sched: |  | 42.75 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
[8 empty] | Total Pages To Go: |  | 36.25 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0
Estimated Final Cost: | 1400478 | Estimated Final Cost: |  |  | 1400478 |  |  | Pages Ahead/(Behind): |  | -0.625 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
Episodic Budget: | 1402236 | Pattern Budget: |  |  | 1500000 |  |  | # Days Scheduled: |  | 7 |  | 2 | 2 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
(Over)/Under Budget: | 1758 | (Over)/Under Pattern: |  |  | 117022 |  |  | # Days To Date: |  | 1
[11 empty] | CREW MEALS |  |  | CUMULATIVE | EXTRAS MEALS |  |  | CUMULATIVE | EXTRA MANDAYS |  |  | CUMULATIVE
[11 empty] | DAY | BDGT | ACTUAL | VARIANCE | DAY | BDGT | ACTUAL | VARIANCE | DAY | BDGT | ACTUAL | VARIANCE
All numbers reflected (OVER)/UNDER | [10 empty] | 1 | 180 | 182 | -2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| (OVER)/UNDER | (OVER)/UNDER | [8 empty] | 2 | 0 | 0 | -2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0
ITEM | TODAY | TO DATE | PAGES |  |  | TOTAL PAY HOURS |  |  | EST.FINAL COST | (OVER)/UNDER | 3 | 0 | 0 | -2 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0
|  |  | DAY | SCHED | ACTUAL | BUDGET |  | ACTUAL | CUMULATIVE | BUDGET | 4 | 0 | 0 | -2 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0
Producers |  | 0 | 1 | 7.125 | 6.5 | 12.5 |  | 11.5 | 1400478 | 1758 | 5 | 0 | 0 | -2 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0
Writers | 0 | 0 | 2 | [7 empty] | 6 | 0 | 0 | -2 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0
Director | 0 | 0 | 3 | [7 empty] | 7 | 0 | 0 | -2 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0
Cast | 100 | 100 | 4 | [7 empty] | 8 | 0 | 0 | -2 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
Stunts | 135 | 135 | 5 | [8 empty] | 180 | 182 | -2 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Casting | 0 | 0 | 6
ATL Tvl/Lvg | 0 | 0 | 7 | [7 empty] | EXTRAS/SI'S $ |  |  | CUMULATIVE | raw stock /foot rate |  |  | 0.301
ATL Fringe | 0 | 0 | [8 empty] | DAY | BDGT | ACTUAL | VARIANCE | dev /foot rate |  |  | 0.09
Extras | 0 | 0 | [8 empty] | 1 | 40 | 33 | 7 | crew lunch rate |  |  | 12.907
Production Staff | 890 | 890 | [8 empty] | 2 | 0 | 0 | 7 | extras lunch rate |  |  | 12.91
Camera | 25 | 25 | [8 empty] | 3 | 0 | 0 | 7
Art Dept | 71 | 71 | [8 empty] | 4 | 0 | 0 | 7
Set Construction | 0 | 0 |  | E.F.C. BEFORE BREAKAGE: |  | 1400478 |  |  | EPISODIC BUDGET: | 1402236 | 5 | 0 | 0 | 7
Set Strike | 0 | 0 | [8 empty] | 6 | 0 | 0 | 7
Set Operations | 0 | 0 |  | BREAKAGE: |  | 17500 | ** |  |  |  | 7 | 0 | 0 | 7
Electric | 60 | 60 | [8 empty] | 8 | 0 | 0 | 7
Special FX | 50 | 50 |  | E.F.C. AFTER BREAKAGE: |  | 1382978 |  |  | PATTERN BUDGET: | 1500000 |  | 40 | 33 | 7
Second Unit | 0 | 0 |  | (OVER)/UNDER EPISODIC: |  | 19258
Set Dressing | 120 | 120 |  | (OVER)/UNDER PATTERN: |  | 117022
Props | 50 | 50
Wardrobe | 20 | 20
M/U-Hair | 30 | 30 |  |  |  | Day Budget |  | Day Usage | (Over)/Under | Cumulative
Prod Sound | 32 | 32
Transportation | 55 | 55 | Raw Stock |  |  | 0 |  | 0 | 0 | 0
Locations/Catering | 120 | 120 | Dev |  |  | 0 |  | 0 | 0 | 0
BTL Fringe | 0 | 0 | Crew Lunches |  |  | 180 |  | 182 | -25.814 | -25.814
Dailies | 0 | 0 | (See Extra Lunches Below)
Post ProdTelecine | 0 | 0
Administr. | 0 | 0
| 0 | 0 | CAST |  |  | Total Budget |  | Total Used | Balance | Daily Total
|  |  | Force Calls |  |  | Included in overtime |  |  |  | 0
TOTAL | 1758 | 1758 | Cast / Stunt Overtime |  |  | 1000 |  | 0 | 1000 | 0
NOTES: |  |  | EXTRAS |  |  | Total Budget |  | Total Used | Balance | Daily Total
|  |  | Lunches (#) |  |  | 0 |  | 0 | 0 | 0
|  |  | ManDays (#) |  |  | 0 |  | 0 | 0 | 0
|  |  | S/I MDays (#) |  |  | 2 |  | 2 | 0 | 2
|  |  | Mandays ($'s) |  |  | 40 |  | 33 | 7 | 33
|  |  | CONSTRUCTION |  |  | Total Budget |  | Total Used | Balance | Daily Total
|  |  | Labor/Box |  |  | 0 |  | 0 | 0 | 0
|  |  | Purchases |  |  | 0 |  | 0 | 0 | 0
|  |  | EXTRA MAN DAYS |  |  | Total Budget |  | Total Used | Balance | Daily Total
|  |  | Grips |  |  | 0 |  | 0 | 0 | 0
|  |  | Electricians |  |  | 0 |  | 0 | 0 | 0
PAGE/SCRIPT NOTES: