## Sheet1
New Production Start Up Checklist
DESCRIPTION | YES/NO | NOTES
Initial Documents (request copies of)
Development Costs
Development Income
Green light paperwork / Commissioning Agreement / Production Agreement
Budget
Delivery requirements
Scripts / Treatment
Schedule & Day out of Days
Insurance documents
Details of Recoupment
Funding Plan:
- Sources of Finance - tax breaks/EIS schemes/Pre sales etc
- Tax Incentives - monitoring of eligible spend
- Primary Licence
- Distribution Advance & Associate Costs - residuals/royalties
- Soft Money
- Cost of Money
- Delivery Requirements
Company Registration Details
Company Year End
Project Set Up
Open Bank Account
Ensure access to On-line Banking
Set up account with Pre Paid Debit cards
Prepare Cash Flow
Obtain Accounting Software Package
Establish Chart Of Accounts (Nominal Ledger Codes)
Set Up Budget on Accounting Software Package
Set Up Supporting Spreadsheets
Set Up Cost Report timetable
Arrange area on shared drive to use
Set Up Payroll & Returns / register if necessary
Obtain VAT details / register if necessary
Set Up Digital Onboarding System
Office & Paperwork
Organise office space for PA and Assistant (where appropriate)
Check IT Connectivity
Set up Purchase Order System
Expenses Forms – Excel (with formulas & up loadable to accounting package)
Float Forms
Casting Advice Notes
SA Timesheets - e-system with agencies or direct bookings
Facility Fee Pads
Journal Vouchers Template
Set up online filing system
Define authorisation procedures
Design stamps for pdf documents
Initial Tasks
Allocation of key tasks between Line Producer & Co-ordinator & Finance Team
Brief Assistant Accountant on their responsibilities
Set Up Cost Control spreadsheets
Agree signatories to Cost Report and frequency
Issue Crew letter
Review special tax arrangements eg Tax credits, Withholding tax etc
Review Treasury & Currency Requirements
Set up list of key contacts & suppliers
Contracts (Crew / Artists) - ensure access to:-
Writers Contracts
Copyright Contracts
Self Employed Contracts
PAYE Contracts
Loan outs Contracts
Artists & Contributors
Supporting Artists
Location Contracts
Contracts & Employment Law - be aware of an financial implications due to:-
- Right to Work procedures
- IR35 Determinations
- Holiday Entitlement
- UK Working Time Directive
- Overtime
- Stakeholder Pension & NEST
- Minimum Wage
- Employment of Children
Financial Information & Reporting
Cash Flow Top Up Request
Cost Reporting
VAT Return
Section 16 Returns
P11d / PSA
Month End Reporting Checklist
Production Asset Register
Useful Documents
Union Agreements applicable:
- Equity
- PACT / Bectu
- Writers Guild of Great Britain
- Musicians Union
US Agreements - SAG, WGA, DGA
Areas to Consider in conjunction with Line Producer
Special deliverables / requirements
Procurement
Credit Card Control
Control of Assets
Carbon Calculator
Data Protection
Bribery Act
Working With Children
Health & Safety
Rights & Clearances
Archive Usage
Blanket Agreements
Recoupment
Insurance:
- Production Package - incl negative cover, cast, director, equipment
- Employers & Public Liability
- Travel Insurance
- Motor Insurance
- Value of applicable Cover
- Excess per claim (deductible)
- Claims - tracking of costs for submission, collating